## Sheet1
|  | Updated on - | 2023-08-16
| East Area WRF O&M |  |  | 3 needed
Spec # | Description | Vendor | Status | hard copy | electronic copy
08331 | Overhead rolling doors | overhead door of atlanta
11134 | SLUDGE GRINDERS | Heyward
11345 | rect chain & flight | Envirex / Heyward | approved
11358 | POLYMER FEED EQUIPMENT | Eco Tech
11512 | SUBMERSIBLE RECESSED IMPELLER PUMPS | Toyo pumps
11513 | DOUBLE DISC PUMPS | Tempelton/Penn valley
11520 | CIRCULAR GRAVITY THICKENER | Envirodyne
11521 | BELT FILTER PRESS | Eco Tech/ alfa laval
14620 | SLUDGE CONVEYORS | Principle Enviormental / serpentix | Out for approval
15100 | VALVES AND APPURTENANCES | Eco Tech
15109 | ELECTRIC MOTOR ACTUATORS, POWERED VALVES AND APPURTENANCES | Eco tech
15650 | SPLIT SYSTEM FAN COIL UNITS | AR Sims
15700 | ELECTRICAL UNIT HEATERS | AR Sims
15750 | ELECTRICAL MAKE-UP AIR HANDLING UNITS | AR Sims
15870 | POWER VENTILATORS | AR Sims
15950 | HVAC CONTROLS | AR Sims
15990 | TESTING, ADJUSTING AND BALANCING OF HVAC SYSTEMS | AR Sims
16155 | Low voltage Magnetic starters
16340 | med. Voltage gear
16361 | low voltage gear
16515 | Adj freq, drives